## ProductBacklog
PRODUCT BACKLOG
Batch 2018_2019
SPRINT BACKLOG | US ID | BACKLOG ITEM |  |  | PRIORITY | RESPONSIBLE | ESTIMATE DATE | REMARKS
|  | AS A/AN | I WANT TO | SO THAT
1 | US1/N1 | Developer | Understand the Problem | l can search for relevant solutions |  |  | 2018-08-06
1 | US1/N2 | Developer | Understand user Stories | l can search for dataset accordingly |  |  | 2018-08-14
1 | US1/N3 | Developer | Download module related to project | l can use them on project |  |  | 2018-08-14
1 | US1/N4 | Developer | List the possible diseases and their symptoms | Research the realated symptoms |  |  | 2018-08-21
1 | US1/N5 | Developer | Get Authorization key | l can fatch data from pridiction |  |  | 2018-08-21
1 | US1/N6 | Developer | find web site for dataset | l can use it |  |  | 2018-08-21
2 | US1/N7 | Developer | Research for the data from the best hospitals (both priv. & Gov.) | Research the realated symptoms |  |  | 2018-08-28
2 | US1/N8 | Developer | download dataset from the various sources | l can train model on it |  |  | 2018-08-28
2 | US1/N9 | Developer | Normalize and clear my data | l can simplify my dataset |  |  | 2018-09-04
2 | US1/N10 | Developer | vectorize my processed data | l can train model on it |  |  | 2018-09-04
2 | US1/N11 | Developer | Train my data on selected model | l can test it's accurisy and perfromance |  |  | 2018-09-04
2 | US1/N12 | Developer | Create datasets to perform operations on a prticular diseas | Integrate the datasets |  |  | 2018-09-04
3 | US1/N13 | Developer | Train my data on random forest model | l can test it's accurisy and perfromance |  |  | 2018-09-11
3 | US1/N14 | Developer | Train my data on multi-layer perception | l can test it's accurisy and perfromance |  |  | 2018-09-11
3 | US1/N15 | Developer | Select those features to remove unwanted dat | Clean the data & Remove the noise |  |  | 2018-09-25
3 | US1/N16 | Developer | Train my data on recurrent neural network | l can test it's accurisy and perfromance |  |  | 2018-09-25
3 | US1/N17 | Developer | calculate accuracy,recall,fvalue and other performance | l can test it's accurisy and perfromance |  |  | 2018-10-02
3 | [6 empty] | 2018-10-02
3 | [6 empty] | 2018-10-02
3 | [6 empty] | 2018-10-02
3 | [6 empty] | 2018-10-02
3 | [6 empty] | 2018-10-02
3 | SB1/US18 | Patient | Register Myself Using Medicovators Mail Id | They Can Receive A Confirmation/Verification Mail |  |  | 2018-10-09
4 | SB1/US19 | Patient | Receive A Confirmation Mail | They Can Access the application |  |  | 2018-12-18
4 | SB1/US20 | Patient | After entering the application | N0w they can go for automatic recommendation of medicines |  |  | 2018-12-18
4 | SB1/US21 | Patient | Login Into The System | They Can View/Edit their Profile |  |  | 2019-01-12
4 | SB1/US22 | Patient | Upload the prescription | I can get the right medicine for me |  |  | 2019-01-20
4 | SB1/US23 | Patient | Enter my age and the symptoms am suffering from | I Can get the right medicine acc. To my age |  |  | 2019-03-08
4 | SB1/US24 | Patient | Enter my sex and the symptoms am suffering from | I Can get the right medicine acc. To my sex |  |  | 2019-03-15
|  | admin | get the best algorithm | so that I can have the best and accurate results
|  | admin | data preparation | so that I have the relevant data
|  | admin | data cleaning | so that the algo. Gives best results
|  | admin | prepare the model | for the application of data on it
|  | admin | daily changes on the final model | to have an update of medicines and best prescription for the patients

## BurnDown chart 1
Date | Planned Task | Actual Uncompleted Task
06 Aug. | 8 | 2
13 Aug. | 5 | 3
20 Aug. | 4 | 2
27 Aug. | 5 | 4
4 Sept. | 2 | 2
11 sept. | 1 | 1
Total | 25 | 14

## SprintBacklog 1
SPRINT BACKLOG 1
US ID | USER STORY | TASK ID | TASKS | TM | STATUS (NOT STARTED / IN PROGRESS / COMPLETED) | ESTIMATED DATE OF TASK COMPLETION
SPRINT 1 - <Data Discovery & Formulation>
SB1/US1 | Understand the Problem | SB1/D1/T1 | l can search for relevant solutions | KS | COMPLETED | 2018-08-06
|  | SB1/D1/T2 | l can search for relevant solutions | AG | COMPLETED | 2018-08-06
|  | SB1/D1/T3 | l can search for relevant solutions | MK | COMPLETED | 2018-08-06
SB1/US2 | Understand user Stories
|  | SB1/D2/T1 | l can search for dataset accordingly |  |  | 2018-08-14
|  | SB1/D2/T2 | l can search for dataset accordingly |  |  | 2018-08-14
|  | SB1/D2/T3 | l can search for dataset accordingly |  |  | 2018-08-14
SB1/D2/T4
SB1/US3 | Download module related to project | SB1/D2/T5 | l can use them on project
|  | SB1/D3/T1 | l can use them on project
|  | SB1/D3/T2 | l can use them on project
SB1/D3/T3
SB1/US6 | List the possible diseases and their symptoms | SB1/D3/T4 | Research the realated symptoms |  |  | 2018-08-14
|  | SB1/D4/T1 | Research the realated symptoms |  |  | 2018-08-14
|  | SB1/D4/T2 | Research the realated symptoms |  |  | 2018-08-14
SB1/D4/T3
SB1/D4/T4
SB1/US7 | Get Authorization key | SB1/D4/T5 | l can fatch data from pridiction |  |  | 2018-08-21
|  | SB1/D5/T1 | l can fatch data from pridiction |  |  | 2018-08-21
|  | SB1/D5/T2 | l can fatch data from pridiction |  |  | 2018-08-21
SB1/D5/T3
SB1/US27 | find web site for dataset | SB1/D5/T4 | l can use it |  |  | 2018-08-21
|  | SB1/D6/T1 | l can use it |  |  | 2018-08-21
|  | SB1/D6/T2 | l can use it |  |  | 2018-08-21
SB1/D6/T3
SB1/D6/T4
SB1/D6/T5

## SprintBacklog 2
SPRINT BACKLOG 2
US ID | USER STORY | TASK ID | TASKS | TM | STATUS (NOT STARTED / IN PROGRESS / COMPLETED) | ESTIMATED DATE OF TASK COMPLETION
SPRINT 2 - <Collection Dataset>
SB2/US1 | Research for the data from the best hospitals (both priv. & Gov.) | SB2/D1/T1 | Research the realated symptoms | KS | COMPLETED | 2018-08-28
|  | SB2/D1/T2 | Research the realated symptoms | AG | COMPLETED | 2018-08-28
|  | SB2/D1/T3 | Research the realated symptoms | MK | COMPLETED | 2018-08-28
SB2/US2 | download dataset from the various sources
|  | SB2/D2/T1 | l can train model on it |  |  | 2018-08-28
|  | SB2/D2/T2 | l can train model on it |  |  | 2018-08-28
|  | SB2/D2/T3 | l can train model on it |  |  | 2018-08-28
SB2/D2/T4
SB2/US3 | Normalize and clear my data | SB2/D2/T5 | l can simplify my dataset |  |  | 2018-09-04
|  | SB2/D3/T1 | l can simplify my dataset |  |  | 2018-09-04
|  | SB2/D3/T2 | l can simplify my dataset |  |  | 2018-09-04
SB2/D3/T3
SB2/US6 | vectorize my processed data | SB2/D3/T4 | can train model on it |  |  | 2018-09-04
|  | SB2/D4/T1 | can train model on it |  |  | 2018-09-04
|  | SB2/D4/T2 | can train model on it |  |  | 2018-09-04
SB2/D4/T3
SB2/D4/T4
SB2/US7 | Train my data on selected model | SB2/D4/T5 | l can test it's accurisy and perfromance |  |  | 2018-09-04
|  | SB2/D5/T1 | l can test it's accurisy and perfromance |  |  | 2018-09-04
|  | SB2/D5/T2 | l can test it's accurisy and perfromance |  |  | 2018-09-04
SB2/D5/T3
SB2/US27 | Create datasets to perform operations on a prticular diseas | SB2/D5/T4 | Integrate the datasets |  |  | 2018-09-04
|  | SB2/D6/T1 | Integrate the datasets |  |  | 2018-09-04
|  | SB2/D6/T2 | Integrate the datasets |  |  | 2018-09-04
SB2/D6/T3
SB2/D6/T4
SB2/D6/T5

## SB Hours 01
Sprint Backlog 1
S. No. | User Story | Tasks | T M | Status | Days Left in Sprint
Hours
EPIC-III : Final Deployment Of Project
1 | As a developer I want to develop the hardware so that Wii-mote can be placed on the screen | Search about the hardware setup
Search about components required
Purchase component from Market
Develop the hardware
2 | As a developer I want to search for applications to be developed so that I can identify an application to be developed | Search annotation application
search paint application
search video making application
search audio recording applications
3 | As a developer I want to study about the technology to be used so I can identify the technology for application | Study tutorials
Study tutorials
start with Basics of c#
start with Basics of c#
4 | As a developer I want to begin coding in swings so I can start with designing of the application | start with Basics of c#
start with Basics of c#
|  | coding of onscreen application |  |  |  | 0
|  | coding of onscreen application |  |  |  | 0
5 | As a developer I want to start coding of my application so that I can develop application | coding of onscreen application |  |  |  | 0
|  | coding of onscreen application |  |  |  | 0
Debug the code
Debug the code
6 | As a developer I want to implement my designed application so that I can use it | Implentation of application on virtual screen.
Implentation of application on virtual screen.
Implentation of application on virtual screen.
Implentation of application on virtual screen.
7 | As a developer I will implement the final project in the classrooms so that system can be used by the users at college | Switch on the projector and set the projected screen
Interface it with PC/laptop
Switch on the projector and set the projected screen
Interface it with PC/laptop
8 | As a tester I will check the whole system implemented in classrooms so that final system could be tested | Callibrate WII remote with virtual screen
Use different applications on the virtual screen
Check the changes made at the virtual screen
Checking if it is working effectively with the laptop and not damaged
9 | As a developer I will prepare the final delivarables of the whole system so that I can give the entire system | Prepare all hardware deliverables
Prepare all software deliverables
Prepare a hardware & software guide
Prepare a user manual & guide for the users
10 | As a developer I want to give training to faculty & students so that they can interact with the system & use it | Giving information to users about the project
Project demonstration
Project demonstration
Project to be operated by different users
| PG | Parth Gupta
| PK | Parv Khandelwal
| NG | Nicky Gupta
| PM | Pankaj Maheshwari
Verified By:
(Product Owner)

## Sprint backlog 3
SPRINT BACKLOG 3
US ID | USER STORY | TASK ID | TASKS | TM | STATUS (NOT STARTED / IN PROGRESS / COMPLETED) | ESTIMATED DATE OF TASK COMPLETION
SPRINT 3
SB3/US1 | Train my data on random forest model | SB3/D1/T1 | l can test it's accurisy and perfromance | KS |  | 2018-09-11
|  | SB3/D1/T2 | l can test it's accurisy and perfromance | AG |  | 2018-09-11
|  | SB3/D1/T3 | l can test it's accurisy and perfromance | MK |  | 2018-09-11
SB3/US2 | Train my data on multi-layer perception | SB3/D2/T1 | l can test it's accurisy and perfromance | KS |  | 2018-09-11
|  | SB3/D2/T2 | l can test it's accurisy and perfromance | AG |  | 2018-09-11
|  | SB3/D2/T3 | l can test it's accurisy and perfromance | MK |  | 2018-09-11
SB3/US3 | Select those features to remove unwanted dat | SB3/D3/T1 | Clean the data & Remove the noise | KS |  | 2018-09-25
|  | SB3/D3/T2 | Clean the data & Remove the noise | AG |  | 2018-09-25
|  | SB3/D3/T3 | Clean the data & Remove the noise | MK |  | 2018-09-25
SB3/US6 | Train my data on recurrent neural network | SB3/D4/T1 | l can test it's accurisy and perfromance | KS |  | 2018-09-25
|  | SB3/D4/T2 | l can test it's accurisy and perfromance | AG |  | 2018-09-25
|  | SB3/D4/T3 | l can test it's accurisy and perfromance | MK |  | 2018-09-25
SB3/US7 | calculate accuracy,recall,fvalue and other performance | SB3/D5/T1 | l can test it's accurisy and perfromance | KS |  | 2018-10-02
|  | SB3/D5/T2 | l can test it's accurisy and perfromance | AG |  | 2018-10-02
|  | SB3/D5/T3 | l can test it's accurisy and perfromance | MK |  | 2018-10-02
SB3/Us8 | Register Myself Using Medicovators Mail Id | SB3/D6/T1 | They Can Receive A Confirmation/Verification Mail | KS |  | 2018-10-09
|  | SB3/D6/T2 | They Can Receive A Confirmation/Verification Mail | AG |  | 2018-10-09
|  | SB3/D6/T3 | They Can Receive A Confirmation/Verification Mail | MK |  | 2018-10-09

## Sprint Backlog 4
SPRINT BACKLOG 4
US ID | USER STORY | TASK ID | TASKS | TM | STATUS (NOT STARTED / IN PROGRESS / COMPLETED) | ESTIMATED DATE OF TASK COMPLETION
SPRINT 4
SB4/US1 | Receive A Confirmation Mail | SB4/D1/T1 | They Can Access the application | KS |  | 2018-12-18
|  | SB4/D1/T2 | They Can Access the application | AG |  | 2018-12-18
|  | SB4/D1/T3 | They Can Access the application | MK |  | 2018-12-18
SB4/US2 | After entering the application | SB4/D2/T1 | Now they can go for automatic recommendation of medicines | KS |  | 2019-01-12
|  | SB4/D2/T2 | Now they can go for automatic recommendation of medicines | AG |  | 2019-01-12
|  | SB4/D2/T3 | Now they can go for automatic recommendation of medicines | MK |  | 2019-01-12
SB4/US3 | Login Into The System | SB4/D3/T1 | They Can View/Edit their Profile | KS |  | 2019-01-19
|  | SB4/D3/T2 | They Can View/Edit their Profile | AG |  | 2019-01-19
|  | SB4/D3/T3 | They Can View/Edit their Profile | MK |  | 2019-01-19
SB4/US4 | Upload the prescription | SB4/D4/T1 | I can get the right medicine for me | KS |  | 2019-02-20
|  | SB4/D4/T2 | I can get the right medicine for me | AG |  | 2019-02-20
|  | SB4/D4/T3 | I can get the right medicine for me | MK |  | 2019-02-20
SB4/US5 | Enter my age and the symptoms am suffering from | SB4/D5/T1 | I Can get the right medicine acc. To my age | KS |  | 2019-03-08
|  | SB4/D5/T2 | I Can get the right medicine acc. To my age | AG |  | 2019-03-08
|  | SB4/D5/T3 | I Can get the right medicine acc. To my age | MK |  | 2019-03-08
SB4/US6 | Enter my sex and the symptoms am suffering from | SB4/D6/T1 | I Can get the right medicine acc. To my sex | KS |  | 2019-03-15
|  | SB4/D6/T2 | I Can get the right medicine acc. To my sex | AG |  | 2019-03-15
|  | SB4/D6/T3 | I Can get the right medicine acc. To my sex | MK |  | 2019-03-15